| Medway Adult Education Service Plan 2023/24 Report Author: admin 8 Generated on: 17 May 2023 |  |
| --- | --- |

| Ref & Action | Planned Start Date | Deadline | Managed By |
| --- | --- | --- | --- |
| MAE23_ Medway Adult Education Service Plan 2023/24 | 01-Apr-2023 | 31-Mar-2024 | Daniel Ratcliff |

|  | Ref & Action | Description | Deadline | Assigned To | Output | Impact | Resources | Milestones/PIs | Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MAE23_01 To deliver a responsive diverse curriculum that meets the needs of the community through quality teaching | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Dan Mace |  |  |  |  |  |

|  |  | Ref & Action | Description | Deadline | Assigned To | Output | Impact | Resources | Milestones/PIs | Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | MAE23_01.01 To maintain processes and systems to meet Ofsted EIF requirements and ensure MAE is a Good provider | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Dan Mace | Processes and systems are in place to meet EIF requirements. Commence preparing for inspection work. |  |  | The Self-Assessment reports indicate a grade 2/Good Review process.es and system and amend if required. Ofsted nominees to attend relevant events as and when they are available to support planning for next Ofsted Inspection. | October 2023 March 2024 |
|  |  | MAE23_01.02 Ensure success rates on accredited foundation English and Mathematics courses are at or above similar providers nationally | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Dan Mace | MAE rates exceed those of similar providers nationally |  |  | Progression pathways developed and monitored. Monitor data outcomes. QRM reports demonstrate good Retention, Attendance, Achievement and Pass rates on completed courses English and Mathematics programme design supports learner progression and achievement. MAE2: % retention rate MAE3: Achievement rate (pass rate) | Monthly QR meetings Monthly QR meetings October 2023 March 2024 |
|  |  | MAE23_01.03 Contribute to Medway’s Digital Transformation agenda with the development of digital systems | -- enter action details here -- | 31-Mar-2024 | Priya Hurkoo; Helen Robinson | Improve efficiencies and customer experience by developing the facilities offered by ebs. Staff are fully engaged with the culture change resulting from the implementation of new ways of working. |  |  | Continue to improve management information by developing a suite of dashboards for staff and the Improvement Board. Prioritise and set up more to workflows to improve automation of processes. Extend use of e-registers. At least 60% of tutors to be using e-registers. Scan all of 21-22 evidence packs onto Management Information System. Redesign and implement digital enrolment journey for ESOL learners. | October 2023 May 2024 March 2024 September 2024 March 2024 |
|  |  | MAE23_01.04 To focus on developing learners’ and apprentices’ knowledge of ‘Prevent’ and British values, so that learners and apprentices understand how they apply to their lives and work | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Dan Mace | Learners and apprentices are able to describe how Prevent and British Values relate to their work and everyday lives |  |  | Compliance monitored through Observations of Teaching, Learning and Assessment. Tutors and Apprenticeship Manager to maintain up- to- date awareness of Prevent and BV. Establish ways to share good practice among tutors. | December 2023 March 2024 |

|  | Ref & Action | Description | Deadline | Assigned To | Output | Impact | Resources | Milestones/PIs | Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MAE23_02 To provide a positive and impactful learning experience to enable progression and achievement | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Dan Mace |  |  |  |  |  |

|  |  | Ref & Action | Description | Deadline | Assigned To | Output | Impact | Resources | Milestones/PIs | Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | MAE23_02.01 Further develop the targeted learning offer, including improved clarity on intent, impact, outcomes and progression | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Helen Robinson | To realise similar levels of targeted enrolments as before Covid19 pandemic and develop further |  |  | Building on current offer to frame a sustainable targeted community learning programme. Undertake targeted marketing campaign and promote to referral partners. Maintain learner evaluation process to identify impact of participation on well-being, mental health and social isolation. | December 2023 June 2024 December 2024 |
|  |  | MAE23_02.02 C Deliver the Medway Adult Education learning programme to boost local skills levels for those furthest from employment | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Dan Mace | MAE has an employability programme which meets local needs identified by partners and supports local recovery plans. |  |  | Develop and design a more holistic programme for employability. Implementation of a holistic programme targeting unemployed and low waged residents. Evaluation used to inform curriculum planning for 2023/24. | September 2023 March 2024 |
|  |  | MAE23_02.03 Review Information, Advice and Guidance (IAG) policy and progression pathways and update as necessary | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Dan Mace | IAG MATRIX developed and maintained to ensure successful accreditation of the IAG Matrix standards |  |  | Progression pathways developed and included in Directory and CIS. Additional staffing resources secured to support IAG processes IAG Matrix accreditation maintained. | Ongoing |
|  |  | MAE23_02.04 Review and revise the methods for engaging learners to contribute feedback on the service | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Dan Mace | Learner feedback is a demonstrable part of our service plans and approaches. |  |  | Learner feedback is received and reviewed regularly. Learners know how to make their views known. | Ongoing |
|  |  | MAE23_02.05 Further develop the curriculum to raise awareness of climate change | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Dan Mace | Curriculum offer to contain educational opportunities to develop understanding of climate change and environmental issues. This will be embedded into some courses and implicit within others. This will be reflected in course programmes, course information sheets and observations |  |  | Further develop curriculum offer. Review curriculum programme. Improve staff awareness of methods to embed into the curriculum. | June 2023 December 2023 October 2024 |
|  |  | MAE23_02.06 Review and revise family learning curriculum to embrace a child friendly city ethos | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Dan Mace | Family learning courses available to support English, Mathematics and, ESOL at venues around Medway to maximise engagement |  |  | Building on current family learning offer to create a sustainable family learning programme. Ensure sufficient resource is in place to deliver family learning. Promote family learning opportunities to maximise engagement. | May 2023 June 2023 March 2024 |

|  | Ref & Action | Description | Deadline | Assigned To | Output | Impact | Resources | Milestones/PIs | Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MAE23_03 To work across Medway with others in partnership to develop new opportunities for growth | -- enter action details here -- | 31-Mar-2024 | Dan Mace; Daniel Ratcliff |  |  |  |  |  |

|  |  | Ref & Action | Description | Deadline | Assigned To | Output | Impact | Resources | Milestones/PIs | Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | MAE23_03.01 Identify new business opportunities to generate additional income | -- enter action details here -- | 31-Mar-2024 | Dan Mace; Daniel Ratcliff | Consultations with businesses will provide future directions and opportunities to develop additional income. |  |  | To review and prioritise findings from business consultations. To allocate resource to research potential opportunities further. To develop and design an offer according to prioritised opportunities. |  |
|  |  | MAE23_03.02 Develop the Apprenticeship Programme to engage other Employers, including non-levy payers | -- enter action details here -- | 31-Mar-2024 | Dan Mace; Daniel Ratcliff | Grow our external apprenticeship provision Apprenticeships delivered in at least 3 external organisations |  |  | Identify apprenticeship standards MAE can deliver. Ensure sufficient resource is in place to deliver apprenticeships. | July 2023 October 2023 March 2024 |
|  |  | MAE23_03.03 Agree and implement the marketing plan to promote our programme offer effectively using a variety of channels | -- enter action details here -- | 31-Mar-2024 | Dan Mace; Daniel Ratcliff | Overall enrolments are increased (2%) and new learners recruited through effective marketing of provision. |  |  | Increase the amount of marketing content generated within the service. Develop yearly campaign planner to further promote courses and provision, in partnership with Corporate Communications team. | March 2024 |
|  |  | MAE23_03.04 Deliver the business plan | -- enter action details here -- | 31-Mar-2024 | Dan Mace; Daniel Ratcliff | A clear and coherent 3- year business plan, providing priorities and objectives for growth and delivery in priority areas. |  |  | Business plan final draft. Business plan endorsed. Delivery commences. | May 2023 September 2023 September 2024 |

|  | Ref & Action | Description | Deadline | Assigned To | Output | Impact | Resources | Milestones/PIs | Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MAE23_04 To attract, retain and develop high performing staff | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Priya Hurkoo |  |  |  |  |  |

|  |  | Ref & Action | Description | Deadline | Assigned To | Output | Impact | Resources | Milestones/PIs | Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | MAE23_04.01 Ensure staff training and development is undertaken to improve staff performance | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Priya Hurkoo | Staff are fully trained for their role and development of existing skills encouraged. |  |  | Systems and process developed to enable staff/tutor CPD centralised records to be accurately maintained and able to produce reports. Provide CPD opportunities to promote the development of outstanding teaching and learning practice. | May 2023 August 2023 March 2024 |
|  |  | MAE23_04.02 Provide opportunities for staff to learn more about how to improve their health and well-being | -- enter action details here -- | 31-Mar-2024 | Geraldine Burden; Priya Hurkoo | Staff are more aware of health and well-being and have access to opportunities to engage with activities. |  |  | Schedule staff well-being programme and deliver a CPD offer. Evaluate the staff well-being programme for impact. | Ongoing March 2024 |

|  | Ref & Action | Description | Deadline | Assigned To | Output | Impact | Resources | Milestones/PIs | Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MAE23_05 C To support the framework of action in the Skills & Employability Plan for Medway | -- enter action details here -- | 31-Mar-2024 | Melanie Phelps; Daniel Ratcliff | Deliver action plan as set out in the Skills & Employability for Medway 2037 (RCE directorate plan) |  |  |  |  |

|  |  | Ref & Action | Description | Deadline | Assigned To | Output | Impact | Resources | Milestones/PIs | Monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | MAE23_05.01 Support the five priorities for action to raise aspirations, realise potential and support sustainable growth | -- enter action details here -- | 31-Mar-2024 | Melanie Phelps; Daniel Ratcliff | Priority skills areas are being consistently delivered against, with positive action taking place. |  |  | To deliver effective interventions against each priority area. | May 2023 August 2023 March 2024 |
|  |  | MAE23_05.02 Raise employers’ aspirations for a productive, skilled, and engaged workforce and increase progression opportunities in work by encouraging businesses to invest in their own workforce | -- enter action details here -- | 31-Mar-2024 | Melanie Phelps; Daniel Ratcliff | Employers engage with our business pledges system, more enterprise advisers are created and more businesses engage with education. |  |  | Number of employers signed up to business pledges increases. Number of Enterprise Advisers increases. | May 2023 August 2023 March 2024 |